## 工作表1
Start | End | Activities | Outputs
2014-02-26 | 2014-03-05 | Analyze Requirement, Install Softwares, Prepare development framework. | Requirment Specification
High Level Design doc
Dev environment ready
2014-03-05 | 2014-03-12 | Detail design, Database design,Function development;Write test case documents. | Low Level Design doc
Database schema ready
Batch-1 function pages (Needs to be specified after discussion)
2014-03-12 | 2014-03-19 | Function development,fix bug, Unit test; Prepare Progress-Report | Tested war package
Progress-Report
2014-03-19 | 2014-03-26 | Develop Batch-2 functions,revise business logic; write test case. | Batch-2 function pages
Test business logic
2014-03-26 | 2014-04-02 | Develop functions, test and fix bugs, write reports. | Batch-2 function pages
Test reports
2014-04-02 | 2014-04-09 | Finish designed functions;test pages and logic, prepare Final-Report. | Final-Report
Finished war package